## Project Timeline
PROJECT TIMELINE |  |  |  | Smartsheet Tip ➜ | [5 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
PROJECT TITLE |  | [Project's title] |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  | DATE | [6 empty] | 2018-03-12
PHASE |  |  | DETAILS | Q2 | [12 empty] | Q3 | [9 empty] | Q4
|  |  |  | APR |  |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP | OCT | NOV | DEC
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Planning |  | - Project Charter | [18 empty] | PROJECT END | bar: APR 2 to APR 16
- Research Questions & Hipothesis | bar: APR 9
- Scope and Goal Setting | bar: APR 16
- Initiation | bar: APR 23
2 | Research & Data Preparation |  | - Raw Data Gathering | bar: APR 23 to APR 30
- Data Licencing | bar: APR 30 to MAY 7
- Work Breakdown Schedule | bar: APR 30 to MAY 7
- Gantt Chart | bar: APR 30 to MAY 7
- Find Problems and Cleaning | bar: APR 30 to MAY 21
- Data Processing to Structured Form | bar: APR 30 to MAY 21
3 | Exploratory Data Analysis |  | - Graphical Methods | bar: APR 30 to MAY 21
- Descriptive statistics | bar: MAY 14 to MAY 28
4 | Statistical Analysis |  | - Meaningful Comparisons | bar: MAY 21 to MAY 28
- Inferential Statistics | bar: MAY 28
- Hypothesis testing | bar: MAY 28
- Limitations of the models
- Evidence Based Recommendation
5 | Machine Learning |  | - Define Analytical problems
- Prediction of features
- Classification
- Clustering
- Sentiment Analysi
- Time series
- Machine Learning strategy
- Supervised Learning
- Unsupervised learning
- Report | bar: APR 16 to MAY 28

## Template Project Timeline
PROJECT TIMELINE TEMPLATE |  |  |  | Smartsheet Tip ➜ | [5 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
PROJECT TITLE |  | [Project's title] |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  | DATE | [6 empty] | 2018-03-12
PHASE |  |  | DETAILS | Q1 | [10 empty] | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  | APR |  | MAY | JUN | JUL |  | AUG | SEP | OCT | NOV | DEC
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Project Conception and Initiation |  | - Project Charter | JAN 16: Project Charter | [7 empty] | PROJECT END
|  |  | - Plan Review | FEB 13: Plan Review
|  |  | - Initiation | [10 empty] | Initiation
2 | Project Definition and Planning |  | - Scope and Goal Setting | [11 empty] | Scope and Goal Setting
|  |  | - Budget | [12 empty] | Budget
- Work Breakdown Schedule
- Gantt Chart
- Communication Plan
- Risk Management
3 | Project Launch & Execution |  | - Status and Tracking
- KPIs
- Quality
- Forecasts
4 | Project Performance & Control |  | - Objective Execution
- Quality Deliverables
- Effort and Cost Tracking
- Performance
5 | Project Close |  | - Postmortem
- Project Punchlist
- Report